## Slide 1
A collaborative effort to implement transfusions in the Woodlands HAL
Tennille Campbell BSN, RN, Lourdes Lujan MSN, RN , Regina Smith MSN, DBA , RN, Krissy Doyle MSN, RN, OCN, NE-BC, Kinjal Patel MSN, RN, CEN, Lilli Ann Mauricio RN, OCN, Megan Phillips BSN, RN
What did we try to accomplish?
Implement and launch a safe and efficient administration of blood product transfusions in the Woodlands Houston Area Location (HAL), which would allow this service for patients within the northeast area. Additionally, this highlighted the collaborative effort between blood bank, lab, and nursing leaders.
How did we know an improvement was made?
Transfusions were successfully started in the Woodlands on February 15, 2022.
Baseline Data
Tis was an initial startup for transfusion services in the Woodlands HAL.
PLAN the improvement
Planning meetings were held with nursing, laboratory, and the blood bank leaders to answer the following questions:
What will be the process to have blood products delivered to Woodlands via courier?
Where to store blood products for optimal temperature?
How to educate nursing lab, and PSC staff on this new process?
How many products can be administered daily?
Creation of transfusion slots in the Ambulatory Treatment Center (ATC) template
How to notify providers that transfusions were now available in the Woodlands location?
Train staff to recognize and mitigate transfusion reactions.
Results Data
Steady growth in number of transfusions. Several patients receiving multiple transfusions on any given day (unique patients).
DO the implementation
Supplies were ordered for area (zebra printer, tubing, coolers/refrigerator for product storage)
Nurses in ATC completed blood product modules in Education Center
Registered nurses travelled to West Houston HAL to observe and learn the transfusion process from product pick up to administration
Couriers were made aware of time constraints and temperature requirements to safely transport blood products to the Woodlands
Email communication was sent out to providers that transfusions would be available in the Woodlands
Templates were created to accommodate 2 slots per day with an increase in slots monthly
Mock “practice” transfusion took place prior to go-live to ensure functionality of all equipment and processes
STUDY the results
Continue to monitor safety reports for adverse reactions, transport issues, storage, delays, needs for more appointments, and communication with Hemo Vigilance Unit (HVU)
Monitor metrics for compliance with documentation (i.e ., Vital sign completion, start/stop time, reactions)
ACT: Maintain/Rollout & future improvement
Report monthly to quality & safety committee
Frontline staff to complete transfusion education yearly
Monitor need for scheduling additional appointments
Discuss future possibility for expansion to same day transfusions
All newly hired staff are oriented to transfusion process