## Slide 1
Nursing Smartphrases to Improve Telehealth Triage
Katrina Riddle RN, BSN, OCN, Courtney Liberty RN, BSN,
Lyvia Tomas RN
Aim Statement
To standardized our telephone and MyChart message triage process in the Sarcoma and Orthopaedic Center. To develop a smart set that will prompt RN to obtain accurate and concise information from patients’ reported symptoms.
Process Improvements
Utilizing feedback from our Advanced Practice Providers and from EPIC MyChart messages in One Connect, We identified the top 3 problems we were experiencing that could be improved on:
1) The lack of consistency and similarity in the documented details of triage questions across the nursing team.
2) Identifying the most common reported patient symptoms and issues that were called or directed into the center.
3) Developing a specific question set for each problem to send to the patient and to the APP for further analysis and documentation.
Changes identified for improvement
On average, the clinical call queue receives 250 patient calls a week during clinic hours. It is important to have structure and develop a system where the nurse can quickly access guidelines and questions when a patient calls with symptoms.
The smart phrases aide in reducing the event of an error due to missing information, especially when the patient calls under stress and has potentially critical symptoms to report. The previous system of relying on each nurses critical thinking skills and question set allowed for a broad range of variables in the questions being asked. This also helps train new clinical nurses who are novice in telephone triage.
Process Analysis
Process Flow Chart- post implementation
Accurate, succinct documentation
Interventions
We formed a work group to brainstorm frequent topics triaged via telephone and MyChart messages.
Utilizing the Telephone Triage for Oncology Nurses : 3rd Edition we researched and created our smartphrases. The goal is to help guide the nurse and patient to obtain all necessary information of their symptoms to send to the provider.
Positive, new developments
Going live – 9/19/22
By implementing this smartphrase system, our nurses are asking the same questions to each patient, so it will be clear, thorough and concise.
We also wanted to make it easy for the patient to understand without using extensive medical terminology.
The current topics that have smartphrases are bleeding, constipation, cough, DVT, diarrhea, dyspnea, fatigue, fever, hand-foot syndrome, nausea and vomiting, mucositis, pain, neuropathy, rash/pruritus and venous access problems.
All triage will be documented in EPIC as a telephone note or MyChart message.
The goal in our telephone triage project is to have the best possible assessment that will contribute to optimal patient outcomes.
By providing our nurses with tools and guidelines to make them successful when speaking with our patients or their family members allows these outcomes to be effective. This exceptional patient care is also noted on our QAPI and Press Ganey scores where patients note being able to speak to a nurse directly and have their problems heard completely.
The relationship between APP and nurse improves when there is clear data and communication to allow a plan of care to be developed and implemented.
Results:
Triage has improved to providers
After our Go Live Date, feedback received from Advanced Practice Providers was positive. Concise, standardized questions covered all bases when triaging patients. Nurse feedback provided was that it created a safety net when patients call with multiple issues, helping them cover all important bases when obtaining critical information.
MyChart and telephone message documentation allows for the clinical team to refer to and identify previous interventions. Patients are also able to view the telephone note or MyChart messages should they have any questions of instructions.
We were able to create a system that allowed all nurses to follow the same triage protocol when speaking to patients and sending to the provider for further intervention if needed.
The new process for triage has been implemented successfully in the center as a standard of practice that all staff follow. We plan to continue and maintain these guidelines and adjust or add to if needed in the future.
We will monitor trending data as it becomes available including number of MyChart messages and telephone triage calls in queue, and patient satisfaction scores via Press Ganey/CAHPS.
ACT: Maintain/Rollout Improvement
- Monitoring documentation to providers and patients via MyChart and Telephone calls. Studying feedback and criticisms in the process from providers and triage nurses.
- Share smart phrases and Telephone Triage for Oncology Nurses: 3rd Edition via PDF with center staff so it is always accessible. Referencing page number in smartphrases.
- Accurate triage is vital and incredibly important to the safety of our severely immunocompromised and fragile patient population who rely on timely and correct intervention and response.