## Slide 1
Controlling Specimen Temperatures During Transport
Ron A. Phipps, Ann C. Reynolds, Waheed N. Muses, Emily M. Walker, Michelle C. Beltran,
Melinda N. Garza, George J. Muppattayil, Bedia A. Barkoh, Clause G. Sawney, Zenaida Richards, Cheryl F. Hirsch-Ginsberg
What did we try to accomplish?
To consistently achieve complete temperature monitoring compliance of samples transported from the HAL’s to the TMC.
Background:
Some laboratory specimens collected at the HAL’s must be transported for analysis to the TMC, and most have Instructions For Use (IFU) requirements for temperature stability.
How did we know improvement was made?
Metrics include the number of shipments, patients and samples impacted by out of compliance temperatures during transit (from specimen pick-up to drop-off).
The target is to have no samples rejected for being out of compliance.
The other metrics are related to costs, including:
Hard costs from specimen re-collection,
Revenue losses from technical and professional charges unable to be completed, and
Soft costs derived from:
  Recollections
  safety events
  rejected tests, and
  the personnel’s evaluation time of specimens placed on hold, and
  the team’s time on implementing corrective actions on the project.
Note that all specimens placed on hold also created patient turnaround time delays.
What changes can we make?
The team focused on the following strategies:
Minimize what needs to be transported
Minimize what needs to be transported via a refrigerator cooler
Improve visibility to temperature measurements in near real time
Minimize temperature fluctuations
Minimize the opening of coolers
Minimize variation between personnel and methods used
Address technical issues with monitoring tags and systems
PLAN the improvement
The team aggressively and systematically determined mitigation plans for a variety of contributing factors to the variations in temperatures to establish a more robust processes and systems, including:
Minimized what needs to be transported as refrigerated
Stopped combining pickups in same cooler (so coolers were not opened prior to TMC arrival)
Standardized back-up process if unable to get readings from primary sensors
Standardized sensor tag placement location in the cooler
Revised measurement method to have the probe in glycol solution rather than reading air temperatures, which better simulate temperature of samples in the cooler.
Ensured that coolers were available at each location so in-process coolers did not have to be opened
Revised how 24-hour urines were prepared and transported, to ensure containers are pre-chilled at least 12 hours prior to transport.
Required that vendor personnel complete adequate training and demonstrated competency before doing routes on their own
Revised contract deliverables/ expectations, and KPI metrics.
Vendor changes:
Implemented real time Command Center monitoring
Minimized variation between personnel & methods used
Addressed technical issues with sensors & systems
Pre-chilled coolers & added new packs at start of routes
STUDY the results
We have achieved and sustained zero specimens out of compliance since interventions were in place in late May!
ACT and Sustain We have been closely monitoring these processes, validating the changes, formalized them into our policies and SOP’s, and updated the contractual KPI’s with the vendor.
The improvements have been sustained for 32 weeks!
April – early May 2023 | Qty
# of Events | 8
# of Packing Lists Impacted | 24
# Patients Impacted | 320
# Patients Recollected | 48
Total Specimens Impacted | 960
# Specimens Rejected | 144
# Tests Impacted | 2,400
# Tests Canceled | 360
Estimated Soft Costs | $286,650
Estimated Hard Costs | $1,200
Estimated Lost Revenue | $36,000
Baseline Data
DO the implementation
Key aspects of the implementation included:
      Improvements to data measuring methods
      Changes to types of sensor hardware used
      Changes in software monitoring system
      Revisions to coolers, cold pack placement and utilization, and sensor placement
      Updated back-up plans and receiving processes
      Changes to documentation availability
      Various improvements to real-time monitoring. .
Escalation with leadership ensured prompt action by MD Anderson and the vendor to resolve the issues.