## Slide 1
Interventional Radiology Expansion of Transperineal Hydrogel Placement for patients with prostate cancer in the Woodlands
Lead: April McBride RT(R), Kathleen Bugarin BSN, MSN, RN, Abigail Sandoval RT(R), Michael Pomares RT (R), Keath Henderson RT(R), Selby Kuruvilla RT(R)(CT)(VI), Sponsors: Thomas Lu MD, Stephen Lee MD, Sanjay Gupta MD, Keenan Harris MHA, RT(R), Jorge Hernandez RT (R)
Aim Statement
The aim of this project is to expand from the TMC location to the Woodlands (WL) IR (Interventional Radiology) procedure area. The goal is start with procedures in the 4th quarter of FY 2022. Expansion of this procedure to the Woodlands will provide additional capacity in collaboration with Radiation Oncology to help meet patient demand.
Base Line Measure/Measures of Success
Prior to 4th quarter of FY 2022 this procedure was not performed at the Woodlands MD Anderson location. The baseline volume for this procedure was zero procedures performed. Successful implementation will be performance of the transperineal placement procedures in WLs IR.
Ishikawa Diagram
An Ishikawa diagram was created to identify potential obstacles to quickly ramp up transperineal placement procedure capacity in IR. From the review of the Ishikawa Diagram, the team identified specific issues that may have inhibited a rapid ramp of this procedure in the IR areas. Interventions were identified and implemented from issues identified using the Ishikawa Diagram.
Ishikawa Diagram
Interventions
The following interventions were implemented, to facilitate the expansion of guided implantation absorbable SpaceOAR and Barrigel hydrogel procedures in IR.
  IR faculty worked with Radiation Oncology to establish a standard referral process.
  IR leadership worked with DI (Diagnostic Imaging) Business Operations and HAL ambulatory logistics leadership to acquire needed equipment, supplies and dedicated human resources. Equipment included: Ultrasound unit, stepper stabilizer and stretcher.
  IR leadership contracted with Barrigel along side Boston Scientific Corporation, to provide product and procedural training to staff and faculty.
  Contracted with equipment provider to provide training for IR technologists, and IR faculty. Training was provided on the US Unit and biplane transducer.
  Established an institution approved process for the High-Level Disinfection of the equipment
  The procedure was introduced into the Woodlands HAL to meet increased patient demand.
Results
The aim statement of this project has been met. Image guided implantation of absorbable transperineal hydrogel placement procedures are now being performed in the Woodlands. Patient volumes in the Woodlands have increased from 0 to 136 patients from the 4th quarter of FY22 to 1st quarter of FY24.
Procedure location offerings have successfully expanded to the Woodlands HAL to meet growing demand and provide convenient access for patients. Multidepartment services including IR, Anesthesia, and Radiation Oncology have been positively impacted by the addition of this capability and capacity.
Patient wait times across the institution have been reduced due to additional capacity brought on-line at the Woodlands.
Financial Impact
From the Woodlands program inception in August 2022 thru November 2023, IR has performed 136 procedures at the WLs campus. Cumulative billing of this procedure has amounted to more than $1.4 million for hospital services since FY22.
Conclusions
IR has successfully increased capacity for image guided implantation of absorbable SpaceOAR and Barrigel hydrogel procedures at the Woodlands location. These procedures are now available at all IR locations at MD Anderson. Procedure scheduling wait times have been reduced and there has been a positive financial and multidepartment volume impact.
Chart: SpaceOAR
Images acquired from Palette Life Sciences
Chart: Hydrogel volume per Qtr.
Chart: Hydrogel volume per Qtr.
| FY22 4th | FY23 1st | FY23 2nd | FY23 3rd | FY23 4th | FY24 1st
Series1 | 4 | 18 | 27 | 30 | 28 | 29