## Slide 1
Implementation of a Triage Nurse Role in a Surgical Oncology Clinic to Improve Patient Access to Care
Rachel McDonald MSN, RN, OCN; Eron Wahid MSN, RN-BC, CNL; Macaela Davis, RN
What did we try to accomplish?
The aim of this project is to implement a Nurse Triage Role in order to increase the patient satisfaction mean scores in the Press Ganey Domain of Access to Care 3 Months, specifically for the access to staff by phone during and after clinic hours, by 10% for surgical oncology patients in the League City HAL by July 2022.
PLAN the improvement
Development of a Triage Nurse Role:
Create position description for Triage Nurse role
Established triage nurse phone line/number
Create education documents for nurse and surgical teams
Results Data
DO the implementation
Education for Triage Nurse
RN completed the Telephone Triage Class
Share RN communication etiquette
Share Triage nurse smart phrases
Share telephone assessment model
Education to PSCs on Triage Nurse Role
Telephone scripting developed for PSC’s
Business manager reinforced periodically
Communication of Triage Nurse Role to surgical teams:
Presented Triage Nurse implementation plan to APP supervisor and CMD for approval
Emailed all surgical teams on Triage Nurse role and purpose
TRIAGE NURSE GO LIVE DATE: JANUARY 10, 2022
Significance
Survey Question: Promptness in Returning Call
We were able to increase our scores in question “promptness in returning calls” by 5%, comparing the 9 months pre and post implementation. We did not meet our initial goal of a 10% increase.
Survey Question: Phone Answered Same Day
We were able to increase our scores in question “phone during office hours answered same day” by 28%, comparing the 9 months pre and post implementation. We met our initial goal of having a 10% increase for this question.
Background
In a surgical oncology clinic, Press Ganey scores have been unfavorable in regard to access to care. Items affecting this score include their ability to access their nurses and/or provider team for problems and questions.
Survey items, such as ease of getting clinic on phone, the clinic’s promptness in returning phone calls, and phone calls answered during same day have all been consistently unfavorable over the past year.
Triage Line CALLS
Considerations
Some patients still prefer to speak directly to the team’s nurse.
Some physicians prefer for their patients not be contacted post surgery by the triage nurse (they already have a process in place).
Noticed the phone incoming line was not utilized consistently.
  This could be attributed to high PSC turn over
  New staff unaware of the Triage Nurse process
Some months did not have survey results for questions addressed, possibly skewing results
.
Notes: Hello!
Our project began with an interest in improving access to healthcare. This is a hot topic and important to our patients. In our League City Surgical Oncology Clinics, we noticed Press Ganey scores were unfavorable for the past year when it came to the “access to care” domains. We developed this project to specifically address the Press Ganey Questions: “ease of getting clinic on the phone, “clinic’s promptness in returning phone calls” and “phone call answered during the same day”.
The aim of our project was to “Implement a Nurse Triage Role in order to increase the patient satisfaction mean scores in the Press Ganey Domain of Access to Care 3 months, specifically for the access to staff by phone during and after clinic hours, by 10% for surgical oncology patients in the League City HAL by July 2022”.
We determined the key functions we wanted the Triage Nurse to address was: 1. Managing the triage nurse phone line-including answering any phone calls and returning all voicemails within 1 hour. 2. Working with primary teams to resolve any issues and 3. call all surgical and specialty new patients, consults and procedures the week following their appointment to determine if there are any new issues that came up that could be addressed. This triage nurse would also assist in other clinics as assigned.
Here are our results:
We depicted both incoming and outgoing calls from our newly established Triage line since implementation. The reasons for incoming calls vary with the majority of calls ranging from a symptom or patient problem. Outgoing calls were made to post-surgical candidates. We made 449 outgoing calls from January to September. The majority report having no issues. While other issues identified were for care questions, scheduling, or symptom management.
Our results data includes the Press Ganey results for Access to Care; in particularly the questions Promptness in Returning Calls, and Phone during office hours answered same day. We were able to increase our scores in question “promptness in returning calls” by 5%, comparing the 9 months pre and post implementation. We did not meet our initial goal of a 10% increase. We were able to increase our scores in question “phone during office hours answered same day” by 28%, comparing the 9 months pre and post implementation. And for this question we were able to meet our initial goal of having a 10% increase.
Things to consider include the fact that some patients still prefer to speak directly to the team’s nurse. They are comfortable with their team and just prefer to speak with them. Also, some physicians prefer for their patients not be contacted post surgery by the triage nurse for they already have a process in place within their team to accomplish this. We also noticed, the triage phone incoming line was not utilized consistently. This could be attributed to high PSC turn over and newer staff unaware of the Triage Nurse process or line. And lastly, some months did not have and Press Ganey survey results for questions addressed, which could possibly have skewed our results.
In conclusion we were very happy with the role out and implementation of our Triage Nurse within our Surgical Oncology clinic. In the future, we hope to consistently and efficiently utilize our Triage Nurse in order to continue improvement in our patients’ access to healthcare.