## Slide 1
Improving Vaccination Rates Among Cancer Patients
Physician champion: Ella Ariza, MD Project Sponsors: Welela Tereffe,MD,CME
Research coordinator: Jennifer Jackson, MS Nurse Manager: Aleza Espinosa MBA-HCM, BSN, CVRN-BC
Department administrator: Kelley Tealer MBA Nursing members: Joleesa Abraham RN, Jimmy Thomas RN,
ASCO Coach: Laura Kaufman, RN,MSN Imelda Alvarado RN, Rebecca Trask RN
Nursing Informatics: Michael Vondenstein, RN
Background
Assessment and recommendations for immunizations is of paramount importance in patients with cancer in order to decrease morbidity and mortality from vaccine preventable infections.
Aim Statement
Phase 1: To improve Influenza and COVID vaccination assessments during new patient visits at the Infectious Diseases outpatient clinic in the next 3 months from 73% non-compliant to 50%.
Phase2: At the infectious disease's outpatient clinic, during Influenza season 2023-2024, we aim to decrease the percentage of patients that do not receive the influenza vaccine from 97% to 87% (10% improvement).
Interventions Made
Phase 1,
March 21st, 2023: Discussed Changes with RNs
April 3rd, 2023: PDSA Cycle1 start
Green Sticker and Smart Phrase
April 11th, 2023 : PDSA Cycle 2
MyChart message to patients "be prepared to share immunization records"
Phase 2
September 14th, PDSA Cycle 1 started
November 2nd, 2023: COVID assessment
Prioritization Matrix
Fishbone
Baseline Run Chart
Phase 1-Immunization assessment ID Clinic Sept--2002-Jan 2023
Changed Data & Outcome Measure
Phase 1
Results Data
Phase 1
Conclusion
-By developing a standard workflow for Influenza immunization assessment in the Infectious Diseases Outpatient Clinic, we successfully met and exceeded our aim of decreasing the percentage of patients that do not receive the influenza vaccine from 97% to 85% (12% improvement).
-We have also improved Influenza vaccine documentation by providers and nurses.
Currently working with our IT team to help retrieve the data on “reasons for no vaccination”.
Long term Goals -To Improve immunization assessment, recommendations and rates within the institution.
Spread vaccination assessment improvements throughout the organization.
To create institutional guidelines for immunization and educational material for providers and patients.
-To establish a centralized vaccination clinic at MD Anderson –currently working on a business plan.
Process Flow Chart Vaccination Assessment and Administration
Chart: %Error using nursing smart phrase-Denominator p Chart
| 45183 | 45184 | 45187 | 45188 | 45189 | 45190 | 45191 | 45201 | 45202 | 45203 | 45204 | 45205
P | 0.16667 | 0 | 0 | 0.11111 | 0.0625 | 0 | 0.14286 | 0.083333 | 0 | 0.066667 | 0.16667 | 0.066667
+2 Sigma | 0.30445 | 0.39688 | 0.39688 | 0.21013 | 0.21795 | 0.30445 | 0.28789 | 0.23909 | 0.25415 | 0.22243 | 0.23909 | 0.22243
+1 Sigma | 0.19287 | 0.23909 | 0.23909 | 0.14572 | 0.14962 | 0.19287 | 0.1846 | 0.16019 | 0.16772 | 0.15187 | 0.16019 | 0.15187
Average | 0.081301 | 0.081301 | 0.081301 | 0.081301 | 0.081301 | 0.081301 | 0.081301 | 0.081301 | 0.081301 | 0.081301 | 0.081301 | 0.081301
-1 Sigma | 0 | 0 | 0 | 0.016884 | 0.012977 | 0 | 0 | 0.0024069 | 0 | 0.010736 | 0.0024069 | 0.010736
-2 Sigma | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UCL | 0.41602 | 0.55466 | 0.55466 | 0.27455 | 0.28627 | 0.41602 | 0.39119 | 0.31798 | 0.34057 | 0.293 | 0.31798 | 0.293
LCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rooming process -> Green sticker for all ID patient’s paperwork as a reminder for the nurses to review and check on Influenza. | -Clinic timing -Nurses to send a note to pharmacy when patient is waiting for vaccination -patients observation time? -Documentation-> Nurses and providers to use vaccination smart phrase to as documentation of assessment and recommendations.
-Patients hesitancy -> Pamphlets and providing education to patients. -Clinic timing -> Influenza high dose available in the ID clinic. | 
High
Impact
Low
Easy
Ease of Implementation
Difficult
Month/ Year | # Influenza vaccine administered in clinic | # Outpatient visits | % of Influenza vaccines administered
Sep-22 | 8 | 460 | 1.74%
Oct-22 | 22 | 466 | 4.72%
Nov-22 | 15 | 461 | 3.25%
Dec-22 | 9 | 440 | 2.05%
Baseline Run Chart
Phase 2-Influenza vaccine administration ID clinic Sept-Dec 2022
Results Data
Phase 2
Chart: % of Workflow Defects in New Patients Infectious Disease Clinic
Chart: Influenza Vaccine Administered ID Clinic
| Influenza Vaccine September 2022 | Influenza Vaccine September 2023 | Influenza Vaccine October 2022 | Influenza Vaccine October 2023 | Influenza Vaccine November 2022 | Influenza Vaccine November 2023 | Influenza Vaccine December 2022 | Influenza Vaccine December 2023
Influenza Vaccine Administered ID Clinic | 8 | 59 | 22 | 75 | 15 | 46 | 9 | 20
Chart: % of Workflow Defects in All ID Clinic Patient Consults u Chart
| 45183 | 45184 | 45187 | 45188 | 45189 | 45190 | 45191 | 45201 | 45202 | 45203 | 45204 | 45205 | 45231 | 45232 | 45233 | 45236 | 45237 | 45261 | 45264 | 45265 | 45266 | 45267
U | 0.29167 | 0.16667 | 0.25 | 0.36111 | 0.26562 | 0.16667 | 0.32143 | 0.14583 | 0.25 | 0.28333 | 0.25 | 0.3 | 0.23333 | 0.35 | 0.37333 | 0.37273 | 0.36364 | 0.49412 | 0.37333 | 0.43529 | 0.34118 | 0.39
+2 Sigma | 0.57443 | 0.67264 | 0.67264 | 0.47422 | 0.48252 | 0.57443 | 0.55684 | 0.50498 | 0.52099 | 0.48728 | 0.50498 | 0.48728 | 0.48728 | 0.48728 | 0.47145 | 0.44808 | 0.44808 | 0.46331 | 0.47145 | 0.46331 | 0.46331 | 0.45348
+1 Sigma | 0.45588 | 0.50498 | 0.50498 | 0.40577 | 0.40992 | 0.45588 | 0.44708 | 0.42115 | 0.42915 | 0.4123 | 0.42115 | 0.4123 | 0.4123 | 0.4123 | 0.40439 | 0.3927 | 0.3927 | 0.40032 | 0.40439 | 0.40032 | 0.40032 | 0.3954
Average | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732 | 0.33732
-1 Sigma | 0.21877 | 0.16966 | 0.16966 | 0.26888 | 0.26472 | 0.21877 | 0.22756 | 0.25349 | 0.24549 | 0.26234 | 0.25349 | 0.26234 | 0.26234 | 0.26234 | 0.27026 | 0.28195 | 0.28195 | 0.27433 | 0.27026 | 0.27433 | 0.27433 | 0.27924
-2 Sigma | 0.10021 | 0.0020004 | 0.0020004 | 0.20043 | 0.19212 | 0.10021 | 0.1178 | 0.16966 | 0.15366 | 0.18736 | 0.16966 | 0.18736 | 0.18736 | 0.18736 | 0.20319 | 0.22657 | 0.22657 | 0.21133 | 0.20319 | 0.21133 | 0.21133 | 0.22116
UCL | 0.69298 | 0.84031 | 0.84031 | 0.54266 | 0.55512 | 0.69298 | 0.6666 | 0.58881 | 0.61282 | 0.56226 | 0.58881 | 0.56226 | 0.56226 | 0.56226 | 0.53852 | 0.50345 | 0.50345 | 0.52631 | 0.53852 | 0.52631 | 0.52631 | 0.51156
LCL | 0 | 0 | 0 | 0.13198 | 0.11952 | 0 | 0.0080428 | 0.085831 | 0.061827 | 0.11238 | 0.085831 | 0.11238 | 0.11238 | 0.11238 | 0.13613 | 0.17119 | 0.17119 | 0.14833 | 0.13613 | 0.14833 | 0.14833 | 0.16308